## Technical Assessment
Security Go Live Technical Assessment
PURPOSE STATEMENT The purpose of this assessment process is to provide the requesting business owner/technical team a succinct guide that covers the technical configurations the security team will assess prior to given approval for go live. **Business owner/technical teams should initiate this process a minimum of 2 weeks before go-live. DOCUMENT STRUCTURE The document compromises at minimum two TABS. This "Assessment Process" TAB and the "Base P1 and P2 Ask" TAB. Other tabs may be added with supporting documentation or data. An example of supporting tabs might be scan result raw data, or pivot tabled charts showing trends in the data, or a recommended list of detailed security configurations which supports the remediation ask before go-live. PROCEDURE / USE Using this document, the Security Team can clearly communicate the "remediation ask" and provide supplementary data, analysis or recommendations in a single remediation tracker. The high level process is; Business/Technical teams requesting go-live assessment the configuration requirements in this document to the systems going live; Security performs an assessment of the system against these same technical configuration requirements; Security issues findings from the assessment that must be remediated before approval for go-live will be issued by Security Team.

## Req'd Security Configs-Windows
PRIORITY 1 (P1) - REMEDIATION ITEMS THE THREAT MANAGEMENT TEAM IS INDICATING SHOULD BE ADDRESSED DIRECTLY OR THROUGH COMPENSATING CONTROLS
Item # | Title/Description | Required Remediation This is the "ASK" by Threat Management for a "net new" system going live | Hostname/IP Server 1 | Hostname/IP Server 2 | Owner(s) Name PM and/or Local Entity Resources
| All of P1 items must be provided to move forward on the assessment **NOTE: TMT will not start an assessment on any host without the P1 Items completed and no MS patches showing |  | <Primary Application Use/ ServerRole> | <Primary Application Use/ ServerRole>
Q1 | Does this system Process, store or transmit EPHI? | Mark Yes or No on ePHI (Patient Information) | Yes/No | Yes/No
Q2 | Does this system Process, store or transmit Credit Card Data? | Mark Yes or No on Credit Card Data | Yes/No | Yes/No
P1 Items
P1.1 | Scanning Request Form | Technical team and Business owner must partner to fill out the required Scanning Request Form. | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.2 | Self Assessment Scan Tool - | Techincal team conducting the build/requesting the go-live assessment provides MBSA report attached to the Remedy ticket showing all MS patches are not missing. | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.3 | Diagram of the ecosystems which shows the relationships between the systems in the ecosystem. Diagram must include ports and protocols needed for production. | Diagram complete w/applications and must include Ports, Protocols, and IP addresses. Provide to TMT to ensure assessment is conducted appropriately | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.4 | 4. Go-Live Self-Assessment Powershell output - showing Passed all checks. (Test-GoLive_v1_X.ps1) | Technical team conducting buil will run the Test-GoLive Powershell script to ensure compliance with TCS 100 Items. | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
Administrative Tasks
P1.5 | All Infrastructure systems must be included into the appropriate IT Support group’s patch management plan that includes patching and reboot schedules, testing procedures, and patching Order of Priority | System(s) part of go-live are programmed in a standard downtime for monthly patching. - Provide Patching cycle from SCCM | To Be completed by Technical Team and Business Owners | To Be completed by Technical Team and Business Owners
P1.6 | Business Owner group and Technical support group are defined for VM tagging | List the business owner(s) AND technical support groups responsible for decision making and IT support of the system after go-live | To Be completed by Technical Team and Business Owners | To Be completed by Technical Team and Business Owners
TMT | Birth Tag on Approval | Add birth Tag to Asset in Nexpose in Asset's actual site | To Be Completed Once in Production | To Be Completed Once in Production
Scan Related Tasks
P1.7 | Security Vulnerability Scan : OS Patching | All OS security patching brought current day of go-live | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.8 | Security Vulnerability Scan : 3rd Party Patching | All 3rd party security patching brought current day of go-live | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.9 | Security Vulnerability Scan : Application | All Application security patching brought current day of go-live | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.10 | Security Vulnerability Scan : Default Password Configuration | TMT will perform this assessment once all TCS is applied. | To Be Verified By Threat Management | To Be Verified By Threat Management
Baseline Build Compliance
P1.11 | Review and implement all configuration requirments in Config Guide |  | To Be Verified By Threat Management | To Be Verified By Threat Management
Configuration Requirements
| Proper OS is installed | All new windows servers shall use 2012R2. If that is not possible, 2008R2 is also acceptable. Any other server Operating System must be approved by exception. (2008 SP2, 2003 R2, etc.). | To Be Verified By Threat Management | To Be Verified By Threat Management
| Server is syncing or in sync with DC time. | DOS prompt. >net time /domain:chi then >net time \\dc. Time should be same (or 1-2 sec diff) | To Be Verified By Threat Management | To Be Verified By Threat Management
| Meets password complexity requirements | Server Manager > Dashboard ¦ Tools ¦ Local Security Policy | To Be Verified By Threat Management | To Be Verified By Threat Management
| Login Banner is set | Domain login banner policy should be effective | To Be Verified By Threat Management | To Be Verified By Threat Management
| Current AV client installed. Current AV Sig Antivirus software should be installed on all windows servers. Use the latest supported version. | SEP Client ¦ Status ¦ Protection definitions are current ¦ Versions ¦ check to ensure curent client and AV sig update dates (Symantec 12.1.7 / McAfee 8.8) | To Be Verified By Threat Management | To Be Verified By Threat Management
| Client pointed to AV Managed Console (SEP/McAfee) | SEP Client ¦ Status ¦ Protection definitions are current ¦ Management ¦ Server value should be an internal IP of a SEPM server | To Be Verified By Threat Management | To Be Verified By Threat Management
| Microsoft Malicious Software Removal Tool (MSRT) should be installed and configured on new servers | MRT.exe installed in c:\windows\system32 (ran also) | To Be Verified By Threat Management | To Be Verified By Threat Management
| Microsoft Enhanced Mitigation Experience Toolkit (EMET) should be installed and configured on new servers | Current Version of EMET is installed (EMET 5.5) | To Be Verified By Threat Management | To Be Verified By Threat Management
| Internet Explorer should be the only installed browser | Internet Explorer shall be the only browser installed. (IE11) | To Be Verified By Threat Management | To Be Verified By Threat Management
| RDP Security Configuration | TCS-100 2.1.2(d)(5.) Session Configuration: End a disconnected session : 60 mins Active Session Limit: Never Idle Session Limit: 5 min When a session limit is reached or connection is broken: Disconnect from Session Remote Configuration: Remote Assistance: Disable Remote Desktop > Select Remote Users > (ensure Administrators and other authorized users are permitted appropriate access) Enable remote access advanced auditing to log events to security event log | To Be Verified By Threat Management | To Be Verified By Threat Management
Logging
| If critical infrastructure, logging centrally to SIEM | If the system is a perimeter device, located in the DMZ, domain controller, authentication server/service, PCI or HIPAA storage or transmission it must centrally log to SIEM | To Be Verified By Threat Management | To Be Verified By Threat Management
| 2.2.2.1.1 Application Log size | Server Manager > Dashboard ¦ Tools ¦ Event Viewer ¦ Application log ¦ right click properties. Should be set to 512000 (500MB) | To Be Verified By Threat Management | To Be Verified By Threat Management
| 2.2.2.1.2 Application FIFO Log queue configuration | Server Manager > Dashboard ¦ Tools ¦ Event Viewer ¦ Application log ¦ right click properties. Should be set to "overwrite events as needed (oldest event first) | To Be Verified By Threat Management | To Be Verified By Threat Management
| 2.2.2.2.1 System Log | Server Manager > Dashboard ¦ Tools ¦ Event Viewer ¦ System log ¦ right click properties. Should be set to 512000 (500MB) | To Be Verified By Threat Management | To Be Verified By Threat Management
| 2.2.2.2.2 System Log FIFO queue configuration | Server Manager > Dashboard ¦ Tools ¦ Event Viewer ¦ System log ¦ right click properties. Should be set to "overwrite events as needed (oldest event first) | To Be Verified By Threat Management | To Be Verified By Threat Management
| 2.2.2.3.1 Security Log | Server Manager > Dashboard ¦ Tools ¦ Event Viewer ¦ Security log ¦ right click properties. Should be set to 512000 (500MB) | To Be Verified By Threat Management | To Be Verified By Threat Management
| 2.2.2.3.2 Security Log queue configuration | Server Manager > Dashboard ¦ Tools ¦ Event Viewer ¦ Security log ¦ right click properties. Should be set to "overwrite events as needed (oldest event first) | To Be Verified By Threat Management | To Be Verified By Threat Management
Auditing
| Account Logon - (Success and Failure) | Audit Other Account Logon Events | To Be Verified By Threat Management | To Be Verified By Threat Management
| Account Management - (Success and Failure) | Audit Other Account Management Events Audit Security Group Management Audit User Account Management | To Be Verified By Threat Management | To Be Verified By Threat Management
| Logon/Logoff - (Success and Failure) | Audit Account Lockout Audit Logoff Audit Logon Audit Other Logon/Logoff Events Audit Special | To Be Verified By Threat Management | To Be Verified By Threat Management
| System - (Success) | Audit Security State Change Audit System Integrity | To Be Verified By Threat Management | To Be Verified By Threat Management
Additional Reviews
P1.13 | Local Users and Groups | Appropriate users and groups setup | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.14 | Events Review | Event Viewer Review | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.15 | UNC/ Shares | Appropriate permissions on shares also on data stored on them | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.16 | Scheduled Tasks Review | Ensure no inappropriate scheduled tasks exist. | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.17 | Server Ports and Services | All unnessecary ports and services must be disabled. | To Be Verified By Threat Management | To Be Verified By Threat Management
Applications
P1.18 | Ensure all applications installed on Server do not contain a Default password | Validate any application default passwords are changed | To Be Verified By Threat Management | To Be Verified By Threat Management
P1.19 | Ensure all applications are logging events correctly | Validate any application default passwords are changed | To Be Verified By Threat Management | To Be Verified By Threat Management
Internet Facing
| Internet Security Checklist must be completed. | Located at: | If Internet Facing Perform these checks | If Internet Facing Perform these checks
| Pre-DMZ Assessment (ports, Services, Ips) | Review Diagram and ports and services open | If Internet Facing Perform these checks | If Internet Facing Perform these checks
| Proper Filtering device infront of Server | All Internet facing systems shall be placed behind a security filtering device such as a firewall, application firewall, or “security router” | If Internet Facing Perform these checks | If Internet Facing Perform these checks
| TLS 1.1 or Greater for Authentication | Use TLS 1.1 or above for all authentication mechanisms and encrypted communications channels | If Internet Facing Perform these checks | If Internet Facing Perform these checks
| Remote services and connections must have appropriate Firewall Rules. | Where SSH/SFTP/FTPS is used on the perimeter anywhere in orgI, Source IP/Port filters are required to establish a ‘whitelist’ for each authorized connection | If Internet Facing Perform these checks | If Internet Facing Perform these checks
| PCI Vulnerabilities (if PCI) | All PCI Vulnerabilities must be remediated. Server must be placed in appropriate bank PCI scanning segment. (internal and external) | If Internet Facing Perform these checks | If Internet Facing Perform these checks
| Post Go-Live Scan (ports, Services, Ips) External Scan | Review Diagram and ports and services open - Once the system is put into production and the CRQ is approved. | If Internet Facing Perform these checks | If Internet Facing Perform these checks
SQL Server
| Database Hardening | Use the approved database configuration technical standards. | If Database is installed | If Database is installed
| MS SQL Audit Feature requirements | (a) Configured to write to the Windows Security Event log (b) Log size 2GB or 30 days activities; whichever is larger (c) Server Audit Specification events (1) All successful and failed logins to each DB (2) SQL service stops/starts (3) Changes to DB sa group (4) DB sa password resets (if possible) (5) Schema changes (6) Creation, Copy, Writing all or some of DB tables/data to a new/other database or to an external file (data exfiltration) (7) Queries across all tables and rows (8) Queue delay not longer than 5 milliseconds | If Database is installed | If Database is installed
| Database Access | Database Ports Restricited to only authorized Connections | If Database is installed | If Database is installed
| Database Accoutns | Only appropriate Accounts are on the databases. | If Database is installed | If Database is installed
Domain Controller
| DC Logging Requirements | 1. Configure all DCs to send logs to SIEM Solution 2. Include all services the Domain Controller is providing (DHCP, DNS, etc.) most notably 3. All Log file sizes should be set to 1GB or greater | If Domain Controller | If Domain Controller
| Admin Management of DC | Remote access sessions to DCs should be video recorded by PAM’s Privileged Session Manager | If Domain Controller | If Domain Controller
DHCP/DNS
| DNS | Logging 1. For DNS servers 2012 R2 or higher, install and configure DNS audit and analytic event logging https://technet.microsoft.com/en-us/library/dn800669.aspx | IF DNS Service is Rrunning | IF DNS Service is Rrunning
| DHCP | 1. Configure DHCP logs to forward to SIEM solution 2. Logging for DHCP should be 30 days rotate logs, FIFO | If DHCP Service is Running | If DHCP Service is Running
Web Server
| Web Config files | ensure no passwords in plaintext | If Web server is installed | If Web server is installed
| Logging General Properties | New Log Time Period: Daily | If Web server is installed | If Web server is installed
| Web Event Logging is configured Appropriately | Extended Properties (a) Date (date): the date on which the request occurred. (b) Time (time): the time, in Coordinated Universal Time (UTC), at which the request occurred. (c) Client IP Address (c-ip): the IP address of the client that made the request. (d) User Name (cs-username): the name of the authenticated user who accessed your server. Anonymous users are indicated by a hyphen. (e) Method (cs-method): the requested action, for example, a GET method. (f) URI Stem (cs-uri-stem): the Universal Resource Identifier, or target, of the action. (g) URI Query (cs-uri-query): the query, if any, that the client was trying to perform. A Universal Resource Identifier (URI) query is necessary only for dynamic pages. (h) Protocol Status (sc-status): the HTTP or FTP status code. (i) Protocol Sub-status (sc-substatus): the HTTP or FTP substatus code. (j) Win32 Status (sc-win32-status): the Windows status code. (k) Protocol Version (cs-version): the protocol version that the client used. (l) Host (cs-host): the host name, if any. (m) User Agent (cs(UserAgent)): the browser type that the client used. | If Web server is installed | If Web server is installed
| Audit/Log retention | Auditing/logging data should be retained for a minimum of 30 days. 90 days is best, 60 days better, 30 days minimum. | If Web server is installed | If Web server is installed
| Remove default web pages | Remove default, sample, and test pages prior to production, (example IIS Admin page) | If Web server is installed | If Web server is installed
| Server Administration | Administer the IIS server via internal RDP connection to the host. (No administrative session directly from the Internet.) | If Web server is installed | If Web server is installed
| Proper Transmission Encryption | HTTPS: Enable only TLS1.2 or above, do not use SSL | If Web server is installed | If Web server is installed

## Req'd Security Configs - Redhat
PRIORITY 1 (P1) - REMEDIATION ITEMS THE SECURITY TEAM IS INDICATING SHOULD BE ADDRESSED DIRECTLY OR THROUGH COMPENSATING CONTROLS
Item # | Title/Description | Required Remediation This is the "ASK" by Threat Management | Hostname/IP | Owner(s) Name PM and/or Local Entity Resources
| All of P1 items must be provided to move forward on the assessment **NOTE: TMT will not start an assessment on any host without the P1 Items completed and no MS patches showing |  | <Primary Application Use/ ServerRole>
Q1 | Does this system Process, store or transmit EPHI? | Mark Yes or No on ePHI (Patient Information) | Yes/No
Q2 | Does this system Process, store or transmit Credit Card Data? | Mark Yes or No on Credit Card Data | Yes/No
P1 Items
P1.1 | Scanning Request Form | Technical team and Business owner must partner to fill out the required Scanning Request Form. | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.2 | Self Assessment Scan Tool - | Techincal team conducting the build/requesting the go-live assessment provides | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.3 | Verify.sh | Technical team conducting buil will run verify.sh | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.4 | Diagram of the ecosystems which shows the relationships between the systems in the ecosystem. Diagram must include ports and protocols needed for production. | Diagram complete w/applications and must include Ports, Protocols, and IP addresses. Provide to TMT to ensure assessment is conducted appropriately | To Be Completed By Technical Team Prior to Requesting Go-Live Assessment
P1.5 | Security Vulnerability Scan : OS Patching | All OS security patching brought current day of go-live | To Be Checked
P1.6 | Security Vulnerability Scan : 3rd Party Patching | All 3rd party security patching brought current day of go-live | To Be Checked
P1.7 | Security Vulnerability Scan : Application | All Application security patching brought current day of go-live | To Be Checked
P1.8 | Security Vulnerability Scan : Default Password Configuration | TMT will perform this assessment once all TCS is applied. | To Be Checked
P1.9 | Baseline Build Compliance
P1.10 | TCS-100 Compliance | Review and implement all configuration requirments in Technical Security Configuration | To Be Checked
2.1 Servers/Infrastructure Devices – General Requirements 4
| 2.1.2.2.2 Syncing Network time. | Time Zone should be UTC unless otherwise required (sudo dpkg-reconfigure tzdata) Time should sync with time.catholichealth.net (vi /etc/ntp.conf and NIST secondary) | To Be Checked
| 2.1.2.3.2 Under Big Fix UNIX Patching | Big Fix Patching | To Be Checked
| 2.1.2.4.3 Meets CHI password complexity requirements | man pam_unix grep PASS_MIN_LEN /etc/login.defs (needs to be 10) grep PASS_MIN_DAYS /etc/login.defs (4 [days]) grep PASS_MAX_DAYS /etc/login.defs (90 [days]) grep PASS_WARN_AGE /etc/login.defs (7 days) grep pam_cracklib /etc/pam.d/system-auth (ucredit=-1) grep pam_cracklib /etc/pam.d/system-auth (ocredit=-1) grep pam_cracklib /etc/pam.d/system-auth (lcredit=-1) grep pam_cracklib /etc/pam.d/system-auth (difok=4) grep pam_faillock /etc/pam.d/system-auth /etc/pam.d/password-auth (deny=3 unlock_time=604800 fail_interval=900) grep password /etc/pam.d/* ¦ grep pam_unix.so ¦ grep sha512 grep 'ENCRYPT_METHOD SHA512' /etc/login.defs (ENCRYPT_METHOD SHA512) All passwords need to be stored in /etc/shadow awk -F: '{if ($2 != "x") print $1 ": Password stored in file!"}' </etc/passwd | To Be Checked
| Check who has UID 0 | If any account other than root has a UID of 0 (awk -F: '($3 == 0) {print}' /etc/passwd)
| File ownership | root must own /etc/shadow or /etc/passwd other than root (ls -l /etc/shadow, ls -l /etc/passwd) | To Be Checked
| File ownership | root must own gshadow and gpasswd (ls -l /etc/gshadow, ls -l /etc/gpasswd) | To Be Checked
| File Permissions on sensitive files | Proper permissions on sensitive files chmod 0000 /etc/shadow chmod 0000 /etc/gshadow chmod 0644 /etc/passwd chmod 644 /etc/group | To Be Checked
| ASLR and EXECshield | sysctl kernel.randomize_va_space or grep kernel.randomize_va_space /etc/sysctl.conf (kernel.randomize_va_space = 2) sysctl kernel.exec-shield or grep kernel.exec-shield /etc/sysctl.conf (kernel.exec-shield = 1) | To Be Checked
| Network Config | net.ipv4.ip_forward = 0 net.ipv4.conf.all.send_redirects = 0 net.ipv4.conf.default.send_redirects = 0 net.ipv4.conf.all.accept_redirects = 0 net.ipv4.conf.default.accept_redirects = 0 net.ipv4.icmp_echo_ignore_broadcasts = 1 net.ipv4.icmp_ignore_bogus_error_responses = 1 net.ipv4.tcp_syncookies = 1 net.ipv4.conf.all.log_martians = 1 net.ipv4.conf.default.log_martians = 1 net.ipv4.conf.all.accept_source_route = 0 net.ipv4.conf.default.accept_source_route = 0 net.ipv4.conf.all.rp_filter = 1 net.ipv4.conf.default.rp_filter = 1 net.ipv6.conf.default.accept_redirects = 0 net.ipv4.conf.all.secure_redirects = 0 net.ipv4.conf.default.secure_redirects = 0 options ipv6 disable=1 | To Be Checked
| Firewall | service iptables status (iptables: Firewall is running) grep ":INPUT" /etc/sysconfig/iptables (:INPUT DROP) | To Be Checked
| Login Banner | MOTD | To Be Checked
| Default password | Validate any application default passwords are changed | To Be Checked
Authentication Required for Single user mode
2.2 UNIX Servers – general requirements for new systems
| 2.2.1.1 Current AV client installed. Current AV Sig | AV Package | To Be Checked
| 2.2.1.1 Client pointed to SEPM box for updates | sudo ./sav manage -p (https://support.symantec.com/en_US/article.HOWTO101768.html#v96002459) | To Be Checked
| 2.2.2.1.1 Logs exist | /var/log/ ls -l auth.log, kern.log, syslog exist | To Be Checked
| 2.2.2.1.2 Application FIFO Log queue configuration | pg /etc/logrotate.conf or pg /var/lib/logrotate/status # rotate log files weekly daily # keep 30 days’ worth of backlogs rotate 30 # create new (empty) log files after rotating old ones create # use date as a suffix of the rotated file dateext #size to rotate at regardless of time size 500M # uncomment this if you want your log files compressed Compress | To Be Checked
| Auditing is running | service auditd status grep num_logs /etc/audit/auditd.conf (num_logs = 5) grep max_log_file /etc/audit/auditd.conf (max_log_file = 10) grep max_log_file_action /etc/audit/auditd.conf (max_log_file_action = rotate) | To Be Checked
| Audit rules | sudo grep -w "/etc/localtime" /etc/audit/audit.rules | To Be Checked
| Audit accounts | sudo egrep -w '(/etc/passwd¦/etc/shadow¦/etc/group¦/etc/gshadow¦/etc/security/opasswd)' /etc/audit/audit.rules | To Be Checked
| audit network changes | sudo egrep -w '(sethostname¦setdomainname¦/etc/issue¦/etc/issue.net¦/etc/hosts¦/etc/sysconfig/network)' /etc/audit/audit.rules | To Be Checked
| Review hosts file | pg /etc/hosts | To Be Checked
Services running
| rhosts | /etc/hosts.equiv or .rhosts in users home directories | To Be Checked
| The telnet service must not be running. | rpm -q telnet-server or check for existence of /etc/telnetrc | To Be Checked
| The rsh-server service must not be running. | rpm -q rsh-server or check for # rsh | To Be Checked
| The rexecd service must not be running. | chkconfig "rexec" --list or rexec | To Be Checked
| The rlogind service must not be running. | chkconfig "rlogin" --list or rlogin | To Be Checked
| The SSH daemon must be configured to use only the SSHv2 protocol. | grep Protocol /etc/ssh/sshd_config (Protocol 2) | To Be Checked
| The SSH daemon must not allow authentication using an empty password. | grep -i PermitEmptyPasswords /etc/ssh/sshd_conf (If no line, a commented line, or a line indicating the value "no" is returned, then the required value is set.) | To Be Checked
| The x86 Ctrl-Alt-Delete key sequence must be disabled. | grep pressed /etc/init/control-alt-delete.override (exec /usr/bin/logger -p security.info "Ctrl-Alt-Delete pressed") | To Be Checked
| The NFS server must not have the insecure file locking option enabled. | grep insecure_locks /etc/exports (if anything is returned) | To Be Checked
| The TFTP daemon must operate in secure mode which provides access only to a single directory on the host file system. | grep "server_args" /etc/xinetd.d/tftp (server_args = -s /var/lib/tftpboot - should have -s option if returned) | To Be Checked
| The snmpd service must not use a default password. | grep -v "^#" /etc/snmp/snmpd.conf¦ grep public (there should be no output) | To Be Checked
| The RPM package management tool must cryptographically verify the authenticity of all software packages during installation. | grep nosignature /etc/rpmrc /usr/lib/rpm/rpmrc /usr/lib/rpm/redhat/rpmrc ~root/.rpmrc (there should be nothing returned) | To Be Checked
Logging
| If critical infrastructure, logging centrally to Splunk (Any PII or HIPAA Data) | If the system is a perimeter device, located in the DMZ, domain controller, authentication server/service, it must centrally log to Splunk. | To Be Checked
P1.6 | Diagram of the ecosystems which shows the relationships between the systems in the ecosystem. Diagram must include ports and protocols needed for production. | Diagram complete and available for TMT to review | To Be Checked
P1.7 | Antivirus configured and reporting | System has the latest AV standard installed, signatures up to date, reporting into the central AV console | To Be Checked
P1.8 | Patching Cycle | System(s) part of go-live are programmed in a standard downtime for monthly patching. | To Be Checked
P1.9 | Business Owner group and Techincal support gropu are defined for VM tagging | List the business owner(s) AND techincal support groups responsible for decision making and IT support of the system after go-live | To Be Checked